## Project Management
| 2012-04-16 | 2012-04-23 | 2012-04-30 | 2012-05-07 | 2012-05-14 | 2012-05-21 | 2012-05-28 | 2012-06-04 | 2012-06-11 | 2012-06-18 | 2012-06-25 | 2012-07-02 | 2012-07-09 | 2012-07-16 | 2012-07-23 | 2012-07-30 | 2012-08-06 | 2012-08-13 | 2012-08-20 | 2012-08-27 | 2012-09-03 | 2012-09-10 | 2012-09-17 | 2012-09-24 | 2012-10-01 | 2012-10-08 | 2012-10-15 | 2012-10-22 | 2012-10-29 | 2012-11-05 | 2012-11-12 | 2012-11-19 | 2012-11-26 | 2012-12-03 | 2012-12-10 | 2012-12-17 | 2012-12-24 | 2012-12-31 | 2013-01-07 | 2013-01-14
Deciding on a new location
1. Sub committee engagement
2 A. Sarah to schedule phone meetings at least 2
1 A. See if we can locate a 3rd viable option
2.Full Board engagement & discussion & sign off
3. Final Decision made
3. Final Decision made cont.
4. New Lease signed
Office Layout and Design
1. Determine Architectural lay out [offices, footprint]
2. Determine Interior design plan [floor plan, colors, furniture, art]
3. Determine what goes (1) to new office (2) recycle (3) storage (4) junk
Make final color , finish and selections for furniture | bar: 2012-04-16 to 2012-08-27; 2012-09-10; 2012-12-10 to 2013-01-14
4. Tech Specifications
Communications
1. Determine message around move
2. Determine how to communicate [what channels-who-when]
outside (partners, constituents)
board & staff
TECH
Wiring in new space
Telephone/Internet Providers
Computer hardware purchases
Program
1. Identify Programatic committee | bar: 2012-04-16 to 2012-07-09; 2012-10-29 to 2013-01-14
2. Determine 1st year messaging | bar: 2012-04-16 to 2012-09-24; 2013-01-07 to 2013-01-14
3. Determine programatic implication [ ? do we want special offering?] | bar: 2012-07-02 to 2013-01-14
Moving Logistics
Gather folks involved in last move for lunch - learning
Schedule/ Timing
Pick moving vendor
Disposal of items not being moved
Give boxes to those that will be out of the office on 12/14/12
New Space
New Furniture
Staff Celebration
Public gathering/celebration
| Who: | Tech |  | MGMT |  | ComCom |  | BRD |  | OPS (Sarah, Dora) |  | Prog Com
| Legend: | ! | needs attention
|  | ? | needs decision
completed

## Staff time off . poss Conflicts
 | time axis 2012-12-01 to 2013-01-31
[12 empty] | PACKING DAY | PACKING DAY | MOVE DAY