## Slide 1: Remote Work: A Case Study
Finance Professionals Network
September 14, 2016

## Slide 2: Context & background
Rising cost of office space
Spacious, beautiful, light-filled office in prime location
Under-utilized space due to staff travel and meetings
Desire to reduce costs not directly related to program
Concerned about timing of lease expiration
Anticipated that significant change would be necessary

## Slide 3: Steps to Successful Change
A model from John Kotter
Create the climate for change
Engage the organization
Implement & sustain the change

## Slide 4: Create the climate for change
Step 1: Establish a sense of urgency
Seven year lease ending September-2015
  Landlord offered ‘below market’ renewal ($59 per sqft for 14k sf = $825k/year)
  Investigated Oakland options (estimated at $43 per sqft for 14k sf = $602k/year)
  Preference for downtown San Francisco location (estimated $65 per sqft for suitable space)
Began to consider how/if we could use rent a smaller space

## Slide 5: Create the climate for change
Step 2: Build the guiding team
Leadership Team: assessed strategic and values choices associated with cost of space
Finance Admin Sub team (FAST): managed the project and logistics
Staff Council: represented staff perspective and supported all aspects of transition – external research, policy formation, design trade-offs, furniture and technology selections, etc.

## Slide 6: Create the climate for change
Step 3: Get the right vision
Space Brainstorm: determine priorities
Branding: incorporate new colors and images into space design
Strategic Planning: clarify organizational priorities and business model

## Slide 7: SPACE BRAINSTORM
Align to Values | Allocate resources fairly & uniformly Each team has green/sustainability goals
Remote Access | Flexibility of remote work & access Away time boundaries Remote is a choice, not for everyone Allow for different schedules, flex office hours
Practices | Less email, more IM Set times for meetings More consciousness of NY/SF work hours Paperless, evaluate what can be discarded/moved/stored Update purchasing practices (sustainable) (Re)Educate staff about policies & procedures Dedicated days/times for all staff (and/or team) to gather

## Slide 8: SPACE BRAINSTORM
Physical Space | Share space with others Relaxed meeting space Maintain parenting rooms Quiet (library) space Sitting/standing desks Maintain/improve bike friendliness Offsite (or NO?) storage Smaller footprint Near public transit
Technology | New computers (laptops with screens) for all Uniform process/platform, greater efficiency Dev & Prog on same platform (SalesForce) Additional (re)training on key systems Collaboration tools for remote access New online space for relationships with grantees, advisors, and donors

## Slide 9: BRANDING

## Slide 10: STRATEGIC PLAN GOAL #5
Embed nimbleness, innovation and collaboration throughout our systems, culture, talent, activities and values.

## Slide 11: Steps to Successful Change
A model from John Kotter
Create the climate for change
Engage the organization
Implement & sustain the change

## Slide 12: Engage the organization
Step 4: Communicate for buy-in
Remote Work Policy
Up to two days remote
Flexibility and autonomy over schedule
Applies to everyone
Optional
Attend team meetings in person

## Slide 13: Engage the organization
Technology Standards
Laptop, headset, keyboard, mouse, power, and software
Support on-site and remote
Training on hardware set-up plus Box, Outlook, Lync, and Salesforce
Consistent onsite set-up
Offered ‘extra’ equipment
Step 5: Empower action

## Slide 14: Engage the organization
New laptops and cubbies
Cloud-based systems (paperless)
Consistent set-up of sit-stand workstations (on-line sign up)
No assigned workstations
Step 6: Ensure short-term wins

## Slide 15: Steps to Successful Change
A model from John Kotter
Create the climate for change
Engage the organization
Implement & sustain the change

## Slide 16: Implement and sustain the change
Allow fully remote
Re-hire former staff
Relocate New York team to WeWork
Step 7: Don’t let up

## Slide 17: Implement and sustain the change
Ongoing training (led by Staff Council)
Incorporate technology standards into performance management process
Recently revised, loosened the desk sign-up policy
Step 8: Make it stick

## Slide 18: Conclusion
Happily ever after...
Beautiful, light-filled office in prime location
Sufficient space for all staff needs (24 workstations and 10 ‘touchdowns’)
Reduced space costs by 50%
Reduced square footage by 66%
Transition was significantly less difficult than expected
Positive effect on culture and productivity